## Sheet1
eBizWiz Menu | EdifyBiz Module | Status | Est. Days | Notes
Party | Contact | Done
Item | Product | Done
Inquiry Entry | Customer Inquiry | Done | 2026-03-29
Quotation Entry | Customer Quotation | Done | 2026-06-09
Order Placed | Purchase Order | Done | 2026-10-09
Order Received | Sales Order | Done | 2026-12-09
Warranty / Non Warranty Sales | Sales Invoice | Done | 14/09/2026
Stock-IN | Stock In | Done | 16/09/2026
Stock-OUT | Stock Out | Done | 17/09/2026
Physical Stock Taking | Physical Stock | Done | 18/092026
Contract Sales | AMC Contract | Done | 20/09/2026
AMC Quotation | AMC Quotation | Pending | 21/09/2026
Call Entry | Complaint | In Progress
Receipt Entry | Payment | Pending | 23/09/2026
Campaign Entry | Campaign | Pending | 25/09/2026
Sales Target on Office / User | Target | Pending | 27/09/2026
Expenses | Expense | Pending | 30/09/2026
Document Attachments | DMS | Pending | 2026-05-10
In Progress